## Slide 1: RWC-Southern Africa
Kick Off pilot phase operation

## Slide 2: Steps towards RWC-SA starting operations
Create center administrative documents folder for the RWC
  Management folders for all associated member state
    Correspondence
Enlist the national focal points (WDQMS) of the SADC region
Register the WDQMS NFP from SADC countries to the Incident Management System for RWC-SA
  (week#44 Oct 2020 - week#48 Nov 2020)

## Slide 3: Steps towards RWC-SA starting operations
Follow up on members that were unable to attend training and arrange virtual training for the nominated WDQMS NFP
  Zimbabwe, Malawi and Zambia (Request PR office to intervene)
PR-level kick off meeting (week#49 or week#50, Dec 2020)
  Agenda to include:
    management support to the WDQMS NFP
    Management support in nomination of OSCAR/Surface NFP
    Management support to the WIGOS NFP on development of N-WIP

## Slide 4: Steps towards RWC-SA starting operations
Kick-off pilot phase operations, January 2021
Asses the data availability and quality issue prominent within SADC region
Prioritise existing issues to address as follows:-
  Unregistered stations
    Stations not registered in OSCAR/surface, but exchanging data internationally
  Silent stations
    Stations that did not send any data for a long period of time
  Stations that send more than 100% of the expected data according to OSCAR/Surface

## Slide 5: Contact Details
For future enquiries contact
Gaobotse Francis Mosetlho
Regional Manager: Free State and North-West
SOUTH AFRICAN WEATHER SERVICE
E-mail: francis.mosetlho@weathersa.co.za
Office Tel: +27 51 433 2301 or +27 51 433 3281
Cell: +27 83 341 4540

## Slide 6: END