## EC & CG Tracking - OPEN
Date | Requested by | Requested by | Description of Request | Assigned lead | Deadline date | Status indicator | Comment (if any)
Year | Entity/Meeting | Resolution/Decision/Action | Free-text | CDP-ET/Secretariat | dd-month-yyyy | e.g. In progress | Free-text
2020 | EC-72 | Decision 11 | SCALING UP EFFECTIVE PARTNERSHIPS AND SCOPE, SCALE AND PROGRESS OF WMO DEVELOPMENT PROJECTS (4) To request the Capacity Development Panel: (a) To identify opportunities and complementarity between all WMO initiatives to strengthen capacity of developing Members when reviewing the WMO Capacity Development Strategy; (b) To develop appropriate guidelines supporting the implementation of the WMO initiatives to strengthen the capacity of developing country Members; (c) To support the independent evaluation of the WMO Secretariat implemented projects; | CDP | NA | In progress | (a) WMO Capacity Development Strategy reviewed and approved by Cg-19 as a Framework (Resolution 36 (Cg-19)). (b) Elaborated the concept for the Consortium of WMO Education and Training Collaborating Partners (CONECT), which was endorsed by EC-75 (Decision 8 (EC-75)). Progress also reported to EC-76 in the Report of the Chair of the Capacity Development Panel (EC-76/INF. 2.5(5)). See item "2. Main activities and achievements (vi)". (c) Progress reported to EC-76 in the Report of the Chair of the Capacity Development Panel (EC-76/INF. 2.5(5)). See item "2. Main activities and achievements (iv)".
2020 | EC-72 | Decision 13 | DEVELOPING AND SUSTAINING CORE COMPETENCIES AND EXPERTISE (1) To request the EC Capacity Development Panel to: (a) Evaluate and recommend processes for the assessment of impacts of education and training initiatives offered by WMO Regional Training Centres, the Secretariat and WMO Education and Training Partners, for selected representative initiatives, to ensure the continuous improvement of education and training initiatives by assessing their value to Members; (b) Review and recommend mechanisms for WMO Regional Training Centres and other WMO Education and Training Partners to ensure and document that their curricula follow WMO standards, as outlined in Technical Regulations, Volume I - General Meteorological Standards and Recommended Practices (WMO-No. 49), regarding implementation of WMO Basic Instructional Packages (BIPs) and competency frameworks, as further detailed in the Guide to the Implementation of Education and Training Standards in Meteorology and Hydrology, volume I – Meteorology (WMO-No. 1083), and the Compendium of WMO Competency Frameworks (WMO-No. 1209); (c) Review outcomes of the WMO Global Campus initiative and recommend additional outcomes and methods for further achievement of its objectives; (d) Finalize the process of reviewing the Basic Instructional Package for Meteorologists (BIP-M) and Basic Instructional Package for Meteorological Technicians (BIP-MT) by evaluating the revision proposals put forward by the expert teams and the input on these proposals derived from Members’ comments, and that it be submitted to Cg-19 for approval; (e) Review the WMO competency frameworks and identify relevant gaps, taking into account the WMO Reform, including competencies in environmental monitoring. | CDP | NA
2021 | EC-73 | Resolution 28 | WMO-IOC Collaborative Strategy Requests SERCOM, INFCOM, the Research Board, the regional associations, the Capacity Development Panel and any other relevant subsidiary body to identify priority implementation actions in support of developing a draft WMO Ocean Implementation Plan.
2021 | EC-73 | Decision 9 | The Executive Council decides to request the Capacity Development Panel: (1) To compile best practices from the National Meteorological and Hydrological Services (NMHSs) considered to be meeting global standards in the delivery of services. This compilation is to be used in the promotion of standards worldwide; (2) To review and update the current competency frameworks as needed and to support the development of new frameworks in areas not yet addressed, with the support of the Education and Training Office, and in order to benefit from the experience and knowledge of WMO Regional Training Centres (RTCs), in close coordination with RTC representatives; (3) To coordinate with the technical commissions (Commission for Weather, Climate, Water and Related Environmental Services and Applications (SERCOM) and Commission for Observation, Infrastructure and Information Systems (INFCOM)) in the development of a capacity development framework to support the implementation of their activities; (4) To develop strategies to foster the engagement of academic and NMHS staff at the local and regional levels with regard to research, the transfer of research to operations, and the application of research to improve operational delivery; (5) To make recommendations on how to foster systematic contributions from academia towards the enhancement of the research-to-operations continuum, which should address approaches to promoting capacity development and service capabilities in weather, climate, hydrology and environment at regional levels through the promotion of collaboration and communication between regional centres such as Regional Specialized Centres, Regional Climate Centres, Regional Training Centres (RTCs), WMO Integrated Global Observing System (WIGOS) Centres, WMO Information System (WIS) Centres, and so forth; (6) To support and review a publication on leadership and management based on experience gained from the training programmes jointly organized by WMO and the Meteorological Service Singapore for Regional Associations II and V since 2018; (7) To support the development of guidelines on best practices for NMHSs in terms of working with development partners/governments with the aim of enhancing knowledge sharing in this area; (8) To contribute to the Fourteenth WMO Education and Training Symposium (SYMET-14), which will be held in 2021, as additional input to the development and promotion of the educational and training activities of the Organization; (9) To conduct an assessment of and to clarify the roles and responsibilities of the different actors as well as the different funding mechanisms involved in WMO capacity development activities; (10) To make recommendations and develop strategies to strengthen sub-regional, regional, inter-regional and other cooperation groups in order to establish synergies at inter- regional and sub-regional levels and to identify training and capacity-building opportunities;
2022 | EC-75 | Decision 4 | Proposed Approaches to the Business Continuity and Contingency Planning (2) To request the Executive Council Capacity Development Panel (CDP), in coordination with the technical commissions, the regional associations, the Research Board, other WMO bodies and partners as necessary to advise on the capacity development component(s) needed to enhance Members’ business continuity and incorporate them into the CDP strategy; |  | No deadline
2023 | EC-76 | Decision 10 | Actions emanating from the External Evaluation of the WMO Governance Reform 3) To request TCC, the Hydrological Coordination Panel, the Panel of Experts on Polar and High-mountain Observations, Research and Services, and the Capacity Development Panel to review their terms of reference and propose amendments, as needed, to the Executive Council; |  | EC-78 | In progress | In the Agenda for discussions in EC-CDP-8
2023 | Cg-19 | Resolution 4 | United Nations Early Warnings for All initiative Requests: (2) The technical commissions, the Research Board, the Capacity Development Panel, and the Hydrological Coordination Panel, under the guidance of the Executive Council, to: (a) Identify high priority activities to address the urgent needs of Members in building effective multi-hazard early warning systems falling within their terms of reference and to incorporate them into their respective work plans for the next financial period; (b) Identify, catalogue, and integrate priority emerging hazards, such as those due to changes in the cryosphere, in support of the development of necessary monitoring and early warning systems for affected Members; (c) Implement the priority activities in a collaborative, coordinated, and synergetic manner; (d) To regularly report progress to the EC for its guidance. |  | Regular report to EC | Not yet started | In the Agenda for discussions in EC-CDP-9
2023 | Cg-19 | Resolution 35 | Scientific Advisory Panel Recommendations with Research Board Appraisal Decides: (2) SAP Recommendation #2 on bridging the gap between global science capabilities and local impact to be further developed by the Capacity Development Panel in partnership with the RB, SERCOM, INFCOM, Regional Associations and other relevant bodies through: a rapid assessment of where existing plans can be leveraged and amplified through alignment with EW4All; a continuation of the Capacity Development Panel’s (CDP) nuanced and pragmatic assessment of developing local capacity; and a concept note to convene programmes that focus attention to encourage regional innovations, the uptake and upscale of existing successful regional innovations, and additional implementation strategies; (7) SAP Recommendation #7 on broadening expertise through education and training to be developed with the leadership of the Education and Training Office to develop partnerships for integrative educational best practices with support from the Capacity Development Panel. |  |  | Not yet started | In the Agenda for discussions in EC-CDP-9
2023 | Cg-19 | Resolution 36 | WMO Capacity Development Strategy (WCDS) Requests the Capacity Development Panel to report to EC on the uptake and use of the WCDF ; |  | EC-78 and beyond | Not yet started | In the Agenda for discussions in EC-CDP-9
2023 | Cg-19 | Resolution 39 | WMO Gender action plan for the nineteenth financial period Requests technical commissions, the Research Board and other relevant WMO bodies to: (1) Continue implementing the Action Plan within their areas of responsibility; (2) Keep the strong efforts on building and nurturing networks of women scientists and technical experts as well as invest in their capacity; (3) To share the results of these efforts with members through presentations or case studies; (4) Ensure regional and gender balance and inclusiveness in all structures and work plans as provided in their terms of reference; (5) Report to the Executive Council and to Congress on progress; | CDP | Report to EC and Congress |  | In the Agenda for discussions in EC-CDP-9. To be discussed as part of ToRs for ETs of CDP.
2023 | EC-77 | Decision 2 | Actions of the Executive Council on decisions adopted by the nineteenth World Meteorological Congress Action referred to the Capacity Development Panel: To keep the WMO Capacity Development Framework and related implementation actions under review in view of the rapidly changing capacity development landscape, and propose updates and adjustments as necessary (RES 36, Cg-19) | CDP | EC-78 and beyond |  | Relates to Resolution 36 (Cg-19). In the Agenda for discussions in EC-CDP-9
2023 | EC-77 | Resolution 1 | WMO Contribution to the Early Warnings for All initiative Requests the subsidiary bodies of the Executive Council (EC) to also include EW4All as a standing agenda item in each session throughout the next financial period and to report back to EC. | CDP | Whole financial period 2024-2027 |  | Relates to Resolution 4 (Cg-19). In the Agenda for discussions in EC-CDP-9
2023 | EC-77 | Resolution 7 | Subsidiary bodies of the Executive Council Requests: (1) The Chairs of the Technical Coordination Committee and Capacity Development Panel to consult their respective members as to the necessity to amend the terms of references of these bodies and submit recommendations, as needed, to the next session of the Council; | CDP | EC-78 |  | In the Agenda for discussions in EC-CDP-8

## CDP Tracking - OPEN
Date | Requested by | Requested by | Description of Request | Assigned lead | Deadline date | Status indicator | Comment (if any)
Year | Entity/Meeting | Resolution/Decision/Action | Free-text | CDP-ET/Secretariat | dd-month-yyyy | e.g. In progress | Free-text
2023 | HCP/CDP-7 |  | The hydrological community under the lead of HCP prepared the WMO Plan of Action for Hydrology, approved by Cg Ext(2021). For each capacity development activity present in the plan, a leading responsibility was assigned and approved by EC 76. CDP leads 12 activities among which 5 need action in 2023. In addition, CDP contributes to 2 other activities. Milestones need to be set for the activities under CDP’s responsibility | CDP |  | Complete | The request raised concerns from CDP Acting Chair and members, regarding the roles assigned to CDP. It was explained that CDP is an advisory body of EC, and that assignments requesting implementation of activities do not fit the Terms of Reference of the Panel. It was suggested that the request may be for advice on partners that could assist implementing the activities. (for more details, see Report CDP-7).
2023 | CDP-7 | Action 1 (CDP-7) | Excerpt of outcomes of the 7th Meeting of the Capacity Development Panel to be added to the INF report associated with relevant CDP document prepared for WMO Congress (Cg-19). | Secretariat | Cg-19 | Complete | Information included in Cg-19/INF. 4.4(3)
2023 | CDP-7 | Action 2 (CDP-7) | IOC Capacity Development Strategy to be shared with CDP members. Actionee(s): Albert Fisher to share the document with ETR for making it available in the CDP-7 web meeting page (Agenda Item 3.6). | Other | 2023-03-31 | Complete | Document uploaded to CDP-7, Agenda Item 3.6.
2023 | CDP-7 | Action 3 (CDP-7) | Secretariat to prepare and maintain a list of “requests for advice” directed to CDP, including status of follow-up actions. Actionee(s): CDP representatives of SERCOM, INFCOM, HCP, RB, JCB, RAs, RTCs, and Expert Team facilitators to share with Secretariat any requests that were received directly. Secretariat to add to list the requests captured from Executive Council and Congress. | CDP | CDP-8 and beyond | Complete | An "Action Tracker" was created.
2023 | CDP-7 | Action 4 (CDP-7) | Add the WCDF Case Studies to the new Capacity Development Programme website Actionee(s): Secretariat: ETR in coordination with the Strategic Communications Unit (SCU) | Secretariat | Aim: Cg-19 | In progress | During Cg-19, printed versions of the case studies were available in the ETR Booth for consultation. On advice from SCU, some brief information about the WCDF and the case studies were added to the EC-CDP website (https://community.wmo.int/en/governance/executive-council/executive-council/capacity-development-panel ). Site has some technical issues being resolved.
2023 | CDP-7 | Action 5 (CDP-7) | Small group to work on an information document containing suggestions for the Panel moving forward and proposal of amendments to the Terms of Reference. Actionee(s): ET facilitators and Acting Chair. | Other | Coordination meeting 21 April 2023 (tentative date) | Complete | Meeting took place. Information contained in the Report of the Chair to EC-76 was considered sufficient as recommendations of the Panel moving forward. An initial review of the Terms of Reference was conducted and contains some proposals for amendments.

## All Actions Tracking - CLOSED
Date | Requested by | Requested by | Description of Request | Assigned lead | Deadline date | Status indicator | Comment (if any)
Year | Entity/Meeting | Resolution/Decision/Action | Free-text | CDP-ET/Secretariat | dd-month-yyyy | e.g. In progress | Free-text
2020 | EC-72 | Decision 12 | RECOMMENDATIONS FOR REVISION OF THE WMO CAPACITY DEVELOPMENT STRATEGY (1) To request the EC Capacity Development Panel to: (a) Review the WMO Capacity Development Strategy, 2015 (WMO-No. 1133), in coordination with the technical commissions, the Research Board, the Joint WMO-IOC Collaborative Board, Regional Associations and other relevant bodies, taking into consideration the WMO reform, regional priorities emerging needs and trends in delivery or support; (b) Take into account the WMO Community Platform for coordination of information and cooperation to better understand the capacity development needs of NMHS in all areas of service delivery; (c) Ensure that the strategy takes into account ways in which the WMO Regional Training Centres, WMO training partners and WMO specialized Centres can increase their support to capacity development initiatives and means in view of COVID-19 effects; (d) Co-opt other experts from WMO and development partners in support of its activities; (e) Work towards a conclusion of this exercise and prepare a report for consideration by the EC-74; (f) Taking into account the concepts of Hydromet Alliance, CSI, SOFF initiatives for their implementation. (g) Encourage training institutions to embrace online training where possible | CDP | EC-74 | Complete | WMO Capacity Development Strategy reviewed and and approved by Cg-19 as a Framework (WCDF).

## CDP Recs
Date | Requested by | Requested by | Description of Recommendation | Assigned lead | Deadline date | Status indicator | Comment (if any)
Year | Entity/Meeting | Recommendation | Free-text | CDP-ET/Secretariat | dd-month-yyyy | e.g. In progress | Free-text
2023 | CDP-7 | 1 (CDP-7) | CDP members to give continuation to the initiative on writing Case Studies to show examples of applying the WCDS framework, with the aim to sustain a growing collection of examples to be continuously shared in the WMO Capacity Development Programme web site. Case studies should be current, highlight link between operation, policy and societal matters, relate to the WMO Strategic Plan and be prepared using the template provided by the TT in 2022. We aim to have at least one case per WMO Regional Association. | TT-WCDS | Continuous effort | In progress
2023 | CDP-7 | 2 (CDP-7) | Secretariat to consult Members about their awareness and use of the WCD framework. This could be included in other surveys conducted by WMO, rather than being a survey on its own. The consultation should start only after at least one year from the WCDS being published. | Secretariat | Continuous effort | Not yet started | The consultation should start only after at least one year from the WCDS being published.

## Indicators
CDP | Not yet started | CDP
ET-PDIM | In progress | ET-PDIM
ET-HRDET | Overdue | ET-HRDET
ET-TDs | Complete | ET-TDs
ET-RMPDA | Cancelled | ET-RMPDA
TT-WCDS |  | TT-WCDS
Secretariat |  | Secretariat
Other