## EC & CG Tracking - OPEN
Date | Requested by | Requested by | Description of Request | Assigned lead | Deadline date | Status indicator | Comment (if any)
Year | Entity/Meeting | Resolution/Decision/Action | Free-text | CDP and Other | dd-month-yyyy | e.g. In progress | Free-text
2021 | EC-73 | Resolution 28 | WMO-IOC Collaborative Strategy Requests SERCOM, INFCOM, the Research Board, the regional associations, the Capacity Development Panel and any other relevant subsidiary body to identify priority implementation actions in support of developing a draft WMO Ocean Implementation Plan. | CDP and Others |  | In progress | Joint effort of ETR and Mar Div implementing the WMO Marine Services Courses. Full implementation (Phases 1 and 2 in all RAs) estimated to 2027. Support from WMO RTCs.
2022 | EC-75 | Decision 4 | Proposed Approaches to the Business Continuity and Contingency Planning (2) To request the Executive Council Capacity Development Panel (CDP), in coordination with the technical commissions, the regional associations, the Research Board, other WMO bodies and partners as necessary to advise on the capacity development component(s) needed to enhance Members’ business continuity and incorporate them into the CDP strategy; | CDP and Others | No deadline | Complete | Suggest closing to continue following with Resolution 11 (EC-78).
2023 | Cg-19 | Resolution 4 | United Nations Early Warnings for All initiative Requests: (2) The technical commissions, the Research Board, the Capacity Development Panel, and the Hydrological Coordination Panel, under the guidance of the Executive Council, to: (a) Identify high priority activities to address the urgent needs of Members in building effective multi-hazard early warning systems falling within their terms of reference and to incorporate them into their respective work plans for the next financial period; (b) Identify, catalogue, and integrate priority emerging hazards, such as those due to changes in the cryosphere, in support of the development of necessary monitoring and early warning systems for affected Members; (c) Implement the priority activities in a collaborative, coordinated, and synergetic manner; (d) To regularly report progress to the EC for its guidance. | CDP and Others | Regular report to EC | In progress | Discussed in EC-CDP-9. See Recommendations 1 and 2 (EC-CDP-9).
2023 | Cg-19 | Resolution 35 | Scientific Advisory Panel Recommendations with Research Board Appraisal Decides: (2) SAP Recommendation #2 on bridging the gap between global science capabilities and local impact to be further developed by the Capacity Development Panel in partnership with the RB, SERCOM, INFCOM, Regional Associations and other relevant bodies through: a rapid assessment of where existing plans can be leveraged and amplified through alignment with EW4All; a continuation of the Capacity Development Panel’s (CDP) nuanced and pragmatic assessment of developing local capacity; and a concept note to convene programmes that focus attention to encourage regional innovations, the uptake and upscale of existing successful regional innovations, and additional implementation strategies; (7) SAP Recommendation #7 on broadening expertise through education and training to be developed with the leadership of the Education and Training Office to develop partnerships for integrative educational best practices with support from the Capacity Development Panel. | CDP and Others | Continuous effort | Complete | Discussed in EC-CDP-9. On Recommendation #2, note Action 1 (EC-CDP-9). On Recommendation #7, this is part of continuous efforts from ETR in close collaboration with EC-CDP, for example, the review and reconfirmation of WMO RTCs.
2023 | Cg-19 | Resolution 36 | WMO Capacity Development Strategy (WCDS) Requests the Capacity Development Panel to report to EC on the uptake and use of the WCDF ; | CDP | EC-78 and beyond | In progress | Discussed in EC-CDP-9. See Agreed conclusions 2 and 3 (EC-CDP-9).Presentation of 2 new case studies in EC-CDP-10, for feedback and inclusion in the online collection.
2023 | Cg-19 | Resolution 39 | WMO Gender action plan for the nineteenth financial period Requests technical commissions, the Research Board and other relevant WMO bodies to: (1) Continue implementing the Action Plan within their areas of responsibility; (2) Keep the strong efforts on building and nurturing networks of women scientists and technical experts as well as invest in their capacity; (3) To share the results of these efforts with members through presentations or case studies; (4) Ensure regional and gender balance and inclusiveness in all structures and work plans as provided in their terms of reference; (5) Report to the Executive Council and to Congress on progress; | CDP and Others | Report to EC and Congress | In progress | Discussed in EC-CDP-9 (see Agreed conclusions 4 and 6 (EC-CDP-9)).Considered as part of revised ToRs approved by EC-78 (see (viii) Provide guidance regarding WMO efforts in gender equality and youth engagement). ToR (viii) will be continuously considered as part of workplan of ET-EPC.
2023 | EC-77 | Decision 2 | Actions of the Executive Council on decisions adopted by the nineteenth World Meteorological Congress Action referred to the Capacity Development Panel: To keep the WMO Capacity Development Framework and related implementation actions under review in view of the rapidly changing capacity development landscape, and propose updates and adjustments as necessary (RES 36, Cg-19) | CDP | EC-78 and beyond | In progress | Relates to Resolution 36 (Cg-19). Discussed in EC-CDP-9. See Agreed conclusions 2 and 3 (EC-CDP-9). Presentation of 2 new case studies in EC-CDP-10, for feedback and inclusion in the online collection.
2023 | EC-77 | Resolution 1 | WMO Contribution to the Early Warnings for All initiative Requests the subsidiary bodies of the Executive Council (EC) to also include EW4All as a standing agenda item in each session throughout the next financial period and to report back to EC. | CDP | Whole financial period 2024-2027 | In progress | Relates to Resolution 4 (Cg-19). Discussed in EC-CDP-9. See Recommendations 1 and 2 (EC-CDP-9).
2024 | EC-78 | Resolution 7 (EC-78) | Requests the president of the Commission for Observation, Infrastructure and Information Systems (INFCOM), Chair of the Research Board (RB) and chairs of other bodies concerned, such as the Capacity Development Panel (CDP): (1) To review the recommendations and statement of IWVA-8 and consider their implication on and, as necessary, integration into respective work plans and priorities; (2) To keep the president of SERCOM apprised of progress in respect of (1) above; Requests the Secretary-General: (2) To support the capacity development of Members with responsibilities on volcanic ash, especially Least Developed Countries (LDC) and Small Island Developing States (SIDS); | Technical Commissions in coord. with CDP | No deadline | Complete | *Focal point in Secretariat: Greg Brock ET-GO update: Secretariat were contacted and noted that as the CDP has a more peer review function, no specific follow-up action or work plan integration is required by the Panel and its subsidiary bodies. This outcome will be included the report of EC-CDP-10.
2024 | EC-78 | Resolution 11 (EC-78) | Requests the technical commissions, in coordination with the Executive Council Capacity Development Panel, to support Members’ implementation of Business Continuity Management through the development of practical training materials that cover their critical service areas and the full value chain of warning services in their countries, including private entities such as ICT companies and mass media in order to maintain the Disaster Risk Reduction function at national level in the face of significant events ; Requests Regional Associations to include Business Continuity Management training, including through Regional Centres, encouraging cooperation among them , in their workplans, and explore possibilities for peer-to-peer assistance between Members ; Requests the Secretary-General to provide the necessary human, financial and technical resources within the approved budgetary provisions [Secretariat]: (a) To develop the requested training materials; (b) To publish the guidelines and subsequently developed training materials available in all WMO official languages; (c) To support Regional Associations in need to organise trainings in Business Continuity Management; | Technical Commissions in coord. with CDP | No deadline | In progress | *Focal point: Cyrille Honoré ET-GO update: A TT has been set up (DRR) to look into the development of training for BCM and they will seek the CDP's guidance.Coordination between the ET-GO, DRR, and ETR started.

## CDP Tracking - OPEN
Date | Requested by | Requested by | Description of Request | Assigned lead | Deadline date | Status indicator | Comment (if any)
Year | Entity/Meeting | Resolution/Decision/Action | Free-text | CDP-ET/Secretariat | dd-month-yyyy | e.g. In progress | Free-text
2024 | EC-CDP-8 | Action 2 (EC-CDP-8) | Regional Office Europe to coordinate with the Research Board for the transfer of information regarding the mapping of regional contributions prepared by the Office. Actionee(s): Ms Natalia Berghi with assistance from Prof Mary Scholes | Other | TBD | In progress
2024 | EC-CDP-9 | Action 1 (EC-CDP-9) | Establish a Task Team (TT) to further discuss how the EC-CDP can contribute to Recommendation #2, specifically in closing the gap between global scientific capabilities and local impact. The Task Team will explore the possibility of identifying Regional Champions to support this effort. Actionee(s): Dr Carla Gulizia with assistance from Secretariat | CDP and Others | Continuous effort | In progress | The intention to create a TT was presented by the Chair of EC-CDP at the Joint Meeting of the Research Board and Scientific Advisory Panel (October 2024). The action was also considered in the discussions of ET-GO. The task in hand will need a continuous effort.

## All Actions Tracking - CLOSED
Date | Requested by | Requested by | Description of Request | Assigned lead | Deadline date | Status indicator | Comment (if any)
Year | Entity/Meeting | Resolution/Decision/Action | Free-text | CDP-ET/Secretariat | dd-month-yyyy | e.g. In progress | Free-text
2020 | EC-72 | Decision 12 | RECOMMENDATIONS FOR REVISION OF THE WMO CAPACITY DEVELOPMENT STRATEGY (1) To request the EC Capacity Development Panel to: (a) Review the WMO Capacity Development Strategy, 2015 (WMO-No. 1133), in coordination with the technical commissions, the Research Board, the Joint WMO-IOC Collaborative Board, Regional Associations and other relevant bodies, taking into consideration the WMO reform, regional priorities emerging needs and trends in delivery or support; (b) Take into account the WMO Community Platform for coordination of information and cooperation to better understand the capacity development needs of NMHS in all areas of service delivery; (c) Ensure that the strategy takes into account ways in which the WMO Regional Training Centres, WMO training partners and WMO specialized Centres can increase their support to capacity development initiatives and means in view of COVID-19 effects; (d) Co-opt other experts from WMO and development partners in support of its activities; (e) Work towards a conclusion of this exercise and prepare a report for consideration by the EC-74; (f) Taking into account the concepts of Hydromet Alliance, CSI, SOFF initiatives for their implementation. (g) Encourage training institutions to embrace online training where possible | CDP | EC-74 | Complete | WMO Capacity Development Strategy reviewed and and approved by Cg-19 as a Framework (WCDF).
2023 | HCP/CDP-7 |  | The hydrological community under the lead of HCP prepared the WMO Plan of Action for Hydrology, approved by Cg Ext(2021). For each capacity development activity present in the plan, a leading responsibility was assigned and approved by EC 76. CDP leads 12 activities among which 5 need action in 2023. In addition, CDP contributes to 2 other activities. Milestones need to be set for the activities under CDP’s responsibility | CDP |  | Complete | The request raised concerns from CDP Acting Chair and members, regarding the roles assigned to CDP. It was explained that CDP is an advisory body of EC, and that assignments requesting implementation of activities do not fit the Terms of Reference of the Panel. It was suggested that the request may be for advice on partners that could assist implementing the activities. (for more details, see Report CDP-7).
2023 | CDP-7 | Action 1 (CDP-7) | Excerpt of outcomes of the 7th Meeting of the Capacity Development Panel to be added to the INF report associated with relevant CDP document prepared for WMO Congress (Cg-19). | Secretariat | Cg-19 | Complete | Information included in Cg-19/INF. 4.4(3)
2023 | CDP-7 | Action 2 (CDP-7) | IOC Capacity Development Strategy to be shared with CDP members. Actionee(s): Albert Fisher to share the document with ETR for making it available in the CDP-7 web meeting page (Agenda Item 3.6). | Other | 2023-03-31 | Complete | Document uploaded to CDP-7, Agenda Item 3.6.
2023 | CDP-7 | Action 3 (CDP-7) | Secretariat to prepare and maintain a list of “requests for advice” directed to CDP, including status of follow-up actions. Actionee(s): CDP representatives of SERCOM, INFCOM, HCP, RB, JCB, RAs, RTCs, and Expert Team facilitators to share with Secretariat any requests that were received directly. Secretariat to add to list the requests captured from Executive Council and Congress. | CDP | CDP-8 and beyond | Complete | An "Action Tracker" was created.
2023 | CDP-7 | Action 5 (CDP-7) | Small group to work on an information document containing suggestions for the Panel moving forward and proposal of amendments to the Terms of Reference. Actionee(s): ET facilitators and Acting Chair. | Other | Coordination meeting 21 April 2023 (tentative date) | Complete | Meeting took place. Information contained in the Report of the Chair to EC-76 was considered sufficient as recommendations of the Panel moving forward. An initial review of the Terms of Reference was conducted and contains some proposals for amendments.
2023 | CDP-7 | Action 4 (CDP-7) | Add the WCDF Case Studies to the new Capacity Development Programme website Actionee(s): Secretariat: ETR in coordination with the Strategic Communications Unit (SCU) | Secretariat | Aim: Cg-19 | Complete | During Cg-19, printed versions of the case studies were available in the ETR Booth for consultation. On advice from SCU, some brief information about the WCDF and the case studies were added to the EC-CDP website (https://community.wmo.int/en/governance/executive-council/executive-council/capacity-development-panel ). Site has some technical issues being resolved.
2024 | EC-CDP-8 | Action 1 (EC-CDP-8) | Task Team to finalize the revision of the Terms of Reference (TORs) of the Panel. Panel members volunteering for the TT: Dr Carla Gulizia, Ms Karen McCourt, Prof Odjugo, Dr Maria Mamaeva, Dr Albert Martis. Actionee(s): TT with assistance from Secretariat | TT_TORs | EC-78 | Complete | Draft TORs shared by TT for CDP members review 8 March. Final version agreed by CDP members 18 March 2024.
2024 | EC-CDP-8 | Action 3 (EC-CDP-8) | Relevant education and training resources to be posted in the EC-CDP-8 Discussion Forum to aid in addressing the questions raised in the presentation made by the Hydrological Forecasting and Capacity Development Unit. Actionee(s): Secretariat and Panel members | Secretariat | ASAP after EC-CDP-8 | Complete | Relevant education and training resources posted in the EC-CDP-8 Discussion Forum on 19 February 2024
2020 | EC-72 | Decision 11 | SCALING UP EFFECTIVE PARTNERSHIPS AND SCOPE, SCALE AND PROGRESS OF WMO DEVELOPMENT PROJECTS (4) To request the Capacity Development Panel: (a) To identify opportunities and complementarity between all WMO initiatives to strengthen capacity of developing Members when reviewing the WMO Capacity Development Strategy; (b) To develop appropriate guidelines supporting the implementation of the WMO initiatives to strengthen the capacity of developing country Members; (c) To support the independent evaluation of the WMO Secretariat implemented projects; | CDP | NA | Complete | (a) WMO Capacity Development Strategy reviewed and approved by Cg-19 as a Framework (Resolution 36 (Cg-19)). (b) Elaborated the concept for the Consortium of WMO Education and Training Collaborating Partners (CONECT), which was endorsed by EC-75 (Decision 8 (EC-75)). Progress also reported to EC-76 in the Report of the Chair of the Capacity Development Panel (EC-76/INF. 2.5(5)). See item "2. Main activities and achievements (vi)". (c) Progress reported to EC-76 in the Report of the Chair of the Capacity Development Panel (EC-76/INF. 2.5(5)). See item "2. Main activities and achievements (iv)".
2020 | EC-72 | Decision 13 | DEVELOPING AND SUSTAINING CORE COMPETENCIES AND EXPERTISE (1) To request the EC Capacity Development Panel to: (a) Evaluate and recommend processes for the assessment of impacts of education and training initiatives offered by WMO Regional Training Centres, the Secretariat and WMO Education and Training Partners, for selected representative initiatives, to ensure the continuous improvement of education and training initiatives by assessing their value to Members; (b) Review and recommend mechanisms for WMO Regional Training Centres and other WMO Education and Training Partners to ensure and document that their curricula follow WMO standards, as outlined in Technical Regulations, Volume I - General Meteorological Standards and Recommended Practices (WMO-No. 49), regarding implementation of WMO Basic Instructional Packages (BIPs) and competency frameworks, as further detailed in the Guide to the Implementation of Education and Training Standards in Meteorology and Hydrology, volume I – Meteorology (WMO-No. 1083), and the Compendium of WMO Competency Frameworks (WMO-No. 1209); (c) Review outcomes of the WMO Global Campus initiative and recommend additional outcomes and methods for further achievement of its objectives; (d) Finalize the process of reviewing the Basic Instructional Package for Meteorologists (BIP-M) and Basic Instructional Package for Meteorological Technicians (BIP-MT) by evaluating the revision proposals put forward by the expert teams and the input on these proposals derived from Members’ comments, and that it be submitted to Cg-19 for approval; (e) Review the WMO competency frameworks and identify relevant gaps, taking into account the WMO Reform, including competencies in environmental monitoring. | CDP | NA | Complete | (a) See publication ETR-27; (b) Continuously supported by CDP with external reviews; (c) CONECT approved and established; (d) BIPs approved by Cg-19; (e) Review conducted by ETR. Revision for updates to start in 2025.
2021 | EC-73 | Decision 9 | The Executive Council decides to request the Capacity Development Panel: (1) To compile best practices from the National Meteorological and Hydrological Services (NMHSs) considered to be meeting global standards in the delivery of services. This compilation is to be used in the promotion of standards worldwide; (2) To review and update the current competency frameworks as needed and to support the development of new frameworks in areas not yet addressed, with the support of the Education and Training Office, and in order to benefit from the experience and knowledge of WMO Regional Training Centres (RTCs), in close coordination with RTC representatives; (3) To coordinate with the technical commissions (Commission for Weather, Climate, Water and Related Environmental Services and Applications (SERCOM) and Commission for Observation, Infrastructure and Information Systems (INFCOM)) in the development of a capacity development framework to support the implementation of their activities; (4) To develop strategies to foster the engagement of academic and NMHS staff at the local and regional levels with regard to research, the transfer of research to operations, and the application of research to improve operational delivery; (5) To make recommendations on how to foster systematic contributions from academia towards the enhancement of the research-to-operations continuum, which should address approaches to promoting capacity development and service capabilities in weather, climate, hydrology and environment at regional levels through the promotion of collaboration and communication between regional centres such as Regional Specialized Centres, Regional Climate Centres, Regional Training Centres (RTCs), WMO Integrated Global Observing System (WIGOS) Centres, WMO Information System (WIS) Centres, and so forth; (6) To support and review a publication on leadership and management based on experience gained from the training programmes jointly organized by WMO and the Meteorological Service Singapore for Regional Associations II and V since 2018; (7) To support the development of guidelines on best practices for NMHSs in terms of working with development partners/governments with the aim of enhancing knowledge sharing in this area; (8) To contribute to the Fourteenth WMO Education and Training Symposium (SYMET-14), which will be held in 2021, as additional input to the development and promotion of the educational and training activities of the Organization; (9) To conduct an assessment of and to clarify the roles and responsibilities of the different actors as well as the different funding mechanisms involved in WMO capacity development activities; (10) To make recommendations and develop strategies to strengthen sub-regional, regional, inter-regional and other cooperation groups in order to establish synergies at inter- regional and sub-regional levels and to identify training and capacity-building opportunities; |  |  | Complete | See Report of the Chair of the Capacity Development Panel EC-76/INF. 2.5(5)
2023 | EC-76 | Decision 10 | Actions emanating from the External Evaluation of the WMO Governance Reform 3) To request TCC, the Hydrological Coordination Panel, the Panel of Experts on Polar and High-mountain Observations, Research and Services, and the Capacity Development Panel to review their terms of reference and propose amendments, as needed, to the Executive Council; | TT_TORs | EC-78 | Complete | In the Agenda for discussions in EC-CDP-8. A Task Team was formed and completed the revision, which was approved by the Panel. The revised TOR was submitted to EC-78 (EC-78/Doc. 7.5).
2023 | EC-77 | Resolution 7 | Subsidiary bodies of the Executive Council Requests: (1) The Chairs of the Technical Coordination Committee and Capacity Development Panel to consult their respective members as to the necessity to amend the terms of references of these bodies and submit recommendations, as needed, to the next session of the Council; | TT_TORs | EC-78 | Complete | In the Agenda for discussions in EC-CDP-8. A Task Team was formed and completed the revision, which was approved by the Panel. The revised TOR was submitted to EC-78 (EC-78/Doc. 7.5).
2024 | EC-CDP-8 | Action 4 (EC-CDP-8) | EC-CDP to establish a Task Team to revise and provide feedback on the draft “Guidelines for Developing a Basic Instruction Plan for Climate Services (BIP-CS)”. Dr Winifred Jordaan to facilitate the work of the TT. Actionee(s): TT with assistance from Secretariat | Secretariat | NA | Cancelled | Following a meeting of the TT facilitator, SERCOM President, representative of the Climate Group (Amir), and ETR, it was agreed that the Climate Group should review existing guidelides already published instead of creating a new document.
2023 | CDP-7 | 1 (CDP-7) | CDP members to give continuation to the initiative on writing Case Studies to show examples of applying the WCDS framework, with the aim to sustain a growing collection of examples to be continuously shared in the WMO Capacity Development Programme web site. Case studies should be current, highlight link between operation, policy and societal matters, relate to the WMO Strategic Plan and be prepared using the template provided by the TT in 2022. We aim to have at least one case per WMO Regional Association. | TT-WCDS | Continuous effort | Complete | Replaced by Agreed Conclusion 1 of EC-CDP-9
2024 | EC-CDP-9 | Action 2 (EC-CDP-9) | ETs will convene online separately to formulate proposals for concrete actions and deliverables to advance the Panel's work. Actionee(s): ET Chairs with assistance from Secretariat | CDP and Others | TBD | Complete | ET facilitators met EC-CDP Chairs and Secretariat for initial coordination in 2024. ET work has since started and continues under the coordination of the facilitators. ET proposals will be presented at EC-CDP-10.

## CDP Recs
Date | Requested by | Recommendation | Description of Recommendation | Assigned lead | Deadline date | Status indicator | Comment (if any)
Year | Entity/Meeting | Recommendation | Free-text | CDP-ET/Secretariat | dd-month-yyyy | e.g. In progress | Free-text
2023 | CDP-7 | 2 (CDP-7) | Secretariat to consult Members about their awareness and use of the WCD framework. This could be included in other surveys conducted by WMO, rather than being a survey on its own. The consultation should start only after at least one year from the WCDS being published. | Secretariat | Continuous effort | Not yet started | The consultation should start only after at least one year from the WCDS being published.
2024 | EC-CDP-9 | 1 (EC-CDP-9) | The Secretariat and EC-PAC should emphasize the importance of Item 6, "Pillar Coordination," under the "Coordination" section of the current EW4All roadmap. In particular, the need for a joint plan across the four pillars, with clearly defined key performance indicators, should be highlighted. | Secretariat
2024 | EC-CDP-9 | 2 (EC-CDP-9) | All partners delivering education and training activities related to EW4All should consult the Competency Frameworks and Standards developed by WMO.
2024 | EC-CDP-9 | 3 (EC-CDP-9) | The WMO Secretariat to update the Capacity Development Programme webpage to serve as a one-stop resource for all capacity development information. This should include information on the Capacity Development Framework (WCDF) and provide links to all related areas, such as education and training, resource mobilization, and other capacity development efforts within WMO. | Secretariat

## Decisions
Date | Meeting | Decision | Description of decision | Comment (if any)
Year | Entity/Meeting | Agreed Conclusion | Free-text | Free-text
2024 | CDP-8 | Agreed conclusion 1 (CDP-8) | EC-CDP to establish a Task Team to work on the revision of the description of the Capacity Development Programme, the Regional Programme, and their subsidiary Programmes.
2024 | CDP-8 | Agreed conclusion 2 (CDP-8) | EC-CDP to finalize the revision of the Terms of Reference prior to defining the Expert Teams and Task Teams for the period 2024-2027.
2024 | CDP-8 | Agreed conclusion 3 (CDP-8) | EC-CDP recognized the potential benefits of establishing collaborations between WMO RTCs and HMEI. It was agreed that the co-development of open-access training resources and events would represent a sustainable approach to enhancing capacity development at national and regional levels.
2024 | CDP-9 | Agreed conclusion 1 (CDP-9) | EC-CDP to prepare a document or article to assist Members to plan for sustaining capacity. This proposal will be discussed by the Expert Teams (ETs) for inclusion in the EC-CDP action plan as appropriate. Additionally, the topic will be included for discussion at the next Symposium on Education and Training (SYMET).
2024 | CDP-9 | Agreed conclusion 2 (CDP-9) | The EC-CDP will continue its efforts to collect case studies from all Regional Associations. The following volunteers have been designated to coordinate the identification of new case studies: • Prof Odjugo – coordinate efforts in RA-I • Prof Karnawati – coordinate efforts in RA-V • Prof Cudennec – coordinate efforts for case studies hydrology • Dr Mamaeva – coordinate efforts for cases in Russian language | Efforts from Prof. Karnawati (RA V): 2 case studies submitted in 2024. To be added to online collection in 2025, after presentation in EC-CDP-10. Efforts from Dr Mamaeva: organized a presentation to education and training partners in Russian.
2024 | CDP-9 | Agreed conclusion 3 (CDP-9) | A group of volunteers will further discuss the establishment of Task Teams (TTs) to focus on specific activities related to promoting the WCDF. Volunteers include Dr. Carla Gulizia, Dr. Daouda, Dr. Winifred Jordaan, Ms. Karen McCourt, and Dr. Albert Martis. The proposed tasks for these TTs could involve organizing webinars, providing website recommendations, and conducting peer reviews of case studies applying the WCDF.
2024 | CDP-9 | Agreed conclusion 4 (CDP-9) | The work of the Panel will be primarily divided into two ETs, each coordinated by two co-chairs. The EC-CDP will operate under this structure for approximately one year, after which the structure will be reviewed (in September 2025, during EC-CDP-11) to assess its feasibility and determine if any adjustments are necessary. Details of the two ETs are as follows: ET 1 - Focused on matters of coordination. • Covers the following items in the EC-CDP ToR: (iii), (iv), (vii), (ix), and (x). • Co-chairs: Ms Karen McCourt and Dr. Albert Martis. • Members: Ms Jennifer Milton, Dr. YU Yubin, Prof. Peter Odjugo, and Prof. Christophe Cudennec. ET 2 – Focused on matters of education, policy, and competency frameworks. • Covers the following items in the EC-CDP ToR: (v), (vi), and (viii). • Co-Chairs: Dr. Maria Mamaeva and Dr. Somenath Dutta. • Members: Dr. Winifred Jordaan, Dr. Toky Nandrasana Ramanakoto , Prof. Peter Odjugo, and Prof. Christophe Cudennec.
2024 | CDP-9 | Agreed conclusion 5 (CDP-9) | All members of the Panel will work collectively on matters related to EC-CDP ToR items (i) and (ii).
2024 | CDP-9 | Agreed conclusion 6 (CDP-9) | The EC-CDP will advise the SYMET organizing committee to include gender discussions in the Agenda of SYMET-15, and will consider organizing a side event dedicated to this important topic.

## Indicators
CDP | Not yet started
ET-EPC | In progress
ET-GO | Overdue
Secretariat | Complete
Technical Commissions in coord. with CDP | Cancelled
CDP and Others
Other
TT_TORs
ET-PDIM
ET-HRDET
ET-TDs
ET-RMPDA
TT-WCDS